## Sheet1
TaskName | Duration | Dependency
Site Preparation | 5
Foundation | 10 | Site Preparation
Framing | 7 | Foundation
Plumbing | 4 | Framing
Electrical | 6 | Framing
Roofing | 5 | Framing
Interior Finishing | 12 | Electrical
Painting | 6 | Interior Finishing
Final Inspection | 3 | Painting